## projects
CPAD Project:
order | project | description | priority | assignee | schedule | status
1
2 | coordinate awos upgrade - site prep, electrical, notam, etc |  | 1 | [5 empty] | #12 - 18
3 |  | coordinate cpaf agreement and funds transfer | 1 | Tina |  | done |  |  | #29 - 40
4 |  | fuel shed clean out and move material to tool shed | 1 |  |  | done |  |  | #56 - 62
5 |  | site prep excavation and post installation | 1 |  |  | done |  |  | #69 - 73
6 |  | electrical work contracted and completed | 1 |  |  | done |  |  | #87 - 110
7 |  | mesotech install and activation | 1 |  |  | done
8 |  | faa inspection and approval | 1 |  |  | done
|  | upgrade computer | 2
9
10 | maintenance
11 |  | fuel pump maintenance - arrange for filters to be replaced | 1 | Dennie |  | done
12 |  | buy new UPS for light shed with online capability, ability to cycle power remotely | 2 | Greg |  | done | x |  | need to install
13 |  | install batteries in anti-collision lights on hill | 1 |  |  |  | x
14 | [6 empty] | x
15 | sell excess equipment |  | 3 | John, Phil |  |  | x | swisher | donated by foundation mark harris cameron park community foundation
16 |  | dispo old tractor | 3 |  |  |  | x | flailer | dave becker
17 |  | place excess equipment on website for bid to get it sold | 3 |  |  |  | x | tractor | victor | talked with Victor, he will take it back
18 |  | flail mower, swisher, one of the walk behind mowers | 3 |  |  |  | x | walk behind | sell facebook marketplace or craigs list?
19
20 | install airport signs |  | 1 | Phil, Mark
21 |  | replace rotted posts and break-away features | 1 |  |  | done
22 |  | install noise abatement signs | 1 |  |  | done
23 |  | identify additional signs needing replacement | 2 | Dennie
28
29 | creek and ditch cleanout |  |  | chris, Dennie |  |  | x
30 |  | excavation to remove sediment in creek bottom at airport entrance |  |  |  | bid received | x
|  | talk to county about having them do work |  |  |  |  | x
31 |  | ditch cleanout at all culverts around runway |  |  |  |  | x
32
33 | vegetation control and tree removal |  | 2 | Phil, Greg
34 |  | community work days coordination |  | Mark, John, Dennie |  | 2 in april |  | monthly
35 |  | mowing, weeding, cleaning runway of debri, spraying, etc | 1 |  |  | 2 in april
36 |  | mowing plan and schedule | 2
37 |  | brush clearing and rock removal
38 |  | spread emergent chemicals - fenceline and around lights, taxiway | 1 |  |  | initial application along taxiway (ineffective)
39 |  | remove trees in creek by cameron park blvd |  |  |  | bid received
40 |  | remove trees along alhambra drive
41
42 | gate renewal and maintenance |  | 3 | Mark
43 |  | distribute new clickers to neighborhood
44 |  | run new wires, reprogramming,
45 |  | lubrication and adjustment preventative maintenance |  |  |  | done |  | both gates on 4/5
46
47 | office computer and data management |  | 2 | Greg, Tina
48 |  | website maintenance - compliance with new california law
49 |  | update website with current board members and positions | 1 |  |  | done
50 |  | post meeting minutes and agendas |  |  |  | done
51 |  | develop cloud secure storage and backup solution for office computer |  |  |  | in work |  | one drive backup done
52 |  | 5s office and archive anything not needed for day to day operation |  | Dennie |  | in work
53 |  | update office procedures manual
54 |  | install wifi in office
55
56 | Pavement maintenance and repair |  | 3 | Greg, Phil |  |  | x
57 |  | Airpark Streets repair |  |  |  |  | x
58 |  | rough patches at entrance - contact county |  |  |  |  | x
59 |  | Airport runway and taxiway repairs |  |  |  |  | x
60 |  | chuck walls hangar ramp repair |  |  |  |  | x
61 |  | sweep runup areas of small rocks |  |  |  | done 4 5 | x
62 |  | sealcoat and crack pavement plan |  |  |  |  | x
63
64 | Community Communication and outreach |  | 3 | John |  |  |  | Coordinate with Dan (FOCA)
65 |  | Newsletter, Website
66 |  | Committees, Cops and Rodders event
|  | press rleases - awos upgrade |  | John |  | done
67 |  | FOCA, Foundation
68
69 | Airport Layout Plan |  | 3 | Chris Silva, Terry Bohlen |  |  | x | talk to Carl |  | ad hock
70 |  | Airport Infrastructure Plan, thru the fence plan |  |  |  |  | x
71 |  | Airport Diagram, AWOS, FAA Cameras |  |  |  |  | x
72 |  | FAA engagement, improvements |  |  |  |  | x
73 |  | grant applications |  |  |  |  | x
74
75 | financial |  |  | Tina
76 |  | renters manage payments and invoices
77 |  | audit
78 |  | bill pay - coordinate with book-keeper |  |  |  | done
79 |  | look at quickbooks for treasurer |  |  |  | eval copy procured
80
81 | compliance, inspections |  |  | Dennie, Tina
82 |  | fuel system - tanks, environmental |  |  |  | on-going
83 |  | fuel pumps wts and measures |  |  |  | done
84 |  | awos annual inspection |  |  |  | done
85 |  | tsa, county and state requests for info and certs |  |  |  | done - on-going
86
87 | Vehicles maintenance |  |  | Dennie/Phil |  |  | x
88 |  | truck - keys, registration, insurance |  |  |  |  | x
89 |  | tractor - keys, paperwork, maintenance plan |  |  |  |  | x
90 |  | zero turn mower - keys, paperwork for warranty, maintenance contract |  |  |  |  | x
91 |  | contracts for tractor maintenance, mower maintenance |  |  |  | 50 hr maintenance completed | x
92 |  | walk behind mower keys, maintenance |  |  |  |  | x
93 |  | swisher key and maintenance |  |  |  |  | x
94 |  | gator atv - keys, maintenance plan |  |  |  |  | x
95
96 | weather cameras |  |  | Mark, Greg |  |  | x
97 |  | weather cameras maintained by cpaf. also maintains wireless internet infrastructure |  |  |  |  | x
98 |  | - equipment located in fuel shed, office, light shed |  |  |  |  | x
|  | - working to put weather cameras on website |  |  |  |  | procuring static ip addresses, modify sofware to put links on website
99
100 | other/parking lot
101 |  | cal fire base plan |  |  |  |  | x
102 |  | draft plan and coordinate with local calfire office |  |  |  |  | x
103 |  | drone keepouot zone |  |  |  |  | x
104 |  | draft policy, work with faa to generate plan |  |  |  |  | x
105 |  | ocular study |  | Dennie |  |  | x
106 |  | coordinate with county |  |  |  |  | x
107 |  | engagement with county (edc and eid) |  |  |  |  | x
108 |  | engagement with faa and caltrans, other gov entities |  |  |  |  | x
109 |  | inspections, regulatory compliance |  |  |  |  | x
110 |  | capital improvement plans and schedule |  |  |  |  | x
111 |  | pavement, pumps, gates, lights, etc
112 |  | replacing the airport manager
113 |  | ad hoc committee - John and Tina have lead |  |  | initial draft complete
114

## actions
date | action | priority | assignee | status
2025-02-24 |  |  |  |  | parking lot
| daily fuel checks |  |  |  | updates to red book
| daily fod checks |  |  |  | hangar rental contact candidates
| awos upgrade coordination |  |  | done
| rentals follow-up |  |  | in work
| financials acct receivable coordinated |  |  | done
| scanner working |  |  | done
signs installed
| creek cleanout |  |  | need bids
emergent spread along fencelines
buy cell phone
buy wireless router
| light shed alarms and reset procedures |  |  | done
board meeting actions and info - posting
computer backup system
2025-04-14
mowing and weeding day - Saturday - John - done
asphalt repair - ask chris to help, mark, dennie - repeat
weed around lights - dennie done
tie down spray weeds, also taxiway cracks - mark - repeat
order signs - dennie - repeat
noise abatement
airport manager parkng spot - dennie order sign - repeat
sign - airport manager parking only
stripe on pavement
clean up hangar 1 paper files mess - repeat
replace or repair air dispenser - done
plan spring burn - permit - dennie - defer
ask fire dept to come watch with their fire truck (damean snow - lives on boeing)
fix walk behind mower - chain, battery - Chris - mark did, - repeat
computer upgrade plan - greg - upgrade in work - repeat
cloud storage - intitated
awos down - work with Mesotech on repair - dennie - fixed, done
awos computer replacement - dennie - new
avman replacement (pos) - Tina working - need status
evaluate square, toast applications
agreed to proceed with square 30 day trial to evaluate