## plan
airport maintenance plan
schedule 1 work day each month
| advertise with airpark residents |  | need calendar with projects for each month
have a plan for each work party
identify a lead
log work accomplished
| post on website |  | communication
| develop work book with instructions |  | review plan at cpad board mtng
post on website as an event each month
for each project need: |  |  | send out reminer email after cpad mtng (week before event)
project description
lead
| tasks | checklists
tools
training
follow-up
integrate maintenance plan with airport manager schedule and tasks
identify support to airport manager for specific tasks

## maintenance
Maintenance and repair plan for airport and airpark streets
| maintenace items and schedule |  |  | frequency
airport
| gates (3) | sensors check |  | monthly
|  | lubricate chain |  | quarterly
|  | align rails |  | yearly
|  | functional check radio activation |  | monthly
|  | gate by office check card reader |  | monthly
| lights | check for burned out, damaged (walk perimeter) |  | monthly
|  | functional check radio activation |  | monthly
windsocks
|  | verify operation |  | monthly
|  | replace |  | yearly
vegetation
|  | weeds around light building |  | spring, fall |  |  | training, supplies, tools,
|  | weeds around wind tee |  | spring, fall |  |  | hire out major mowing?
|  | weeds around lights |  | monthly | during summer
|  | mowing |  | monthly | during summer
|  | vegetation around hangars |  | spring, fall
|  | weeds around signs |  | monthly
clear tie down area
anti-collision lights on the hill
|  | battery state | load test | yearly
|  | functional check |  | monthly
fuel pumps
|  | air |  | monthly
|  | grounding |  | monthly
hazmat check
tie downs
|  | clean, no locks left behind |  | yearly
signs
|  | legible |  | yearly |  | signs on gates
install new ones correct colors
crack sealing
|  | worst areas in critical traffic areas |  | yearly | spring time
airpark
| signs | condition, trim bushes around them |  | yearly
install new ones
| storm drains |  |  | fall, after major storms
| debri on road |  |  | monthly
airport manager actions
inspections
fuel pump maintenance
etc
burn days

## repairs
repairs needed and plan
anti-collision lights
battery box lock for anti-collision lights
battery preventative maintenance (replace)
north gate
replace signal wire with twisted pair
wind socks
|  | inspect | replace as needed
new signs
|  | airport | order, install
|  | airpark | install
| cracks in high traffic areas |  | weed, clean out cracks, reseal (local patch from home depo)
taxiway to runway
north gate turnaround
south gate approach
equipment
|  | mower deck | lube, check out, pump up tires, operate
|  | weed sprayer | "

## project template
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | gates
project | lead | tasks | tools/supplies | training | follow-up | lube
gates | joe | clean and lubricate | chain lub, grease gun | operation and maintenance manual |  | inspect
Column3: check stops | adjust | chains, stop
|  | check and adjust rails | laser tracker, wrenches
|  | check and adjust chain slack | tape measure, wrenches | allowable slack
signs airpark
wrenches
bolst, nuts, washers
shovel and pick
hacksaw
prunning shears
weeding
weedeaters
clippers, prunning shears
shovel, pick
bags
4 wheeler or truck and trailer
leafblower

## calendar
first Saturday of the month, tied to prior month cpad board mtng
april
may | 6 | signs, windsocks, weeding tie downs and wind tee, approach lights, check gates, lubricate
june | 3
july | 1
august | 5
sept | 2
oct | 7
nov | 4
dec | 2

## may 6 projects
May 6, 8 am, meet at south gate
project | location and actions | Column1 | tools | supplies | training | completion status | follow -up
gates maintenance
| lubricate chains |  |  | chain oil
| adjust chain tension |  | wrenches
| inspect rails, rollers | adjust ht and spacing if needed | wrenches, laser tracker, tape measure
repair screen on gate near office
weeding
| wind tee |  | weed trimmer
| approach lights |  | "
| taxi way entrances | including taxi lights | "
tie downs
| check condition | useable?
| weed around |  | weed trimmer
| remove chains, locks |  | bolt cutters, cutoff grinder
signs
| airpark | replace stop signs | wrenches | bolts,nuts, washers
|  | replace no parking signs | " | "
|  | trim vegetaton around signs | weed trimmer, shears
| airport | weed around signs | weed trimmer
runway inspection
walk runway perimeter
identify weeds, cracks needing immediate attention
| photograph |  | map
prioritize for next work day
windsock inspection
verify movement
look for tears
| photograph | do we need to order replacements?

## mowing calcs
airport grass dimensions
| width | length | sq ft | acres
north | 200 | 500 | 100000 | 2.2957
rw area | 350 | 4000 | 1400000 | 32.1396
south | 350 | 500 | 175000 | 4.0174
runway pavement | 50 | 4000 | 200000 | 4.5914
total grass area |  |  | 1475000 | 33.8613
mower calcs:
mowing speed |  | 5 | 7
deck width |  | 60 | 72
efficiency factor |  | 0.8 | 0.8
sq ft/hr |  | 105600 | 177408
acr/hr |  | 2.4242 | 4.0727
total time to mow, hrs |  | 13.9678 | 8.3142